## Sheet1
Sprint 2 Backlog
Team 5 - Kurtis Mulgrew, Rory Duthie, Calum Duncan and Neil Archibald
To do
In progress
Completed
Task Description | Duriation in hours | Who | Status | Monday | Tuesday | Wednesday | Thursday | Friday | Monday | Tuesday
1. Rank Shares total price in lowest to highest order
Write acceptance test | 1 | Neil | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0
Pair programming, write unit test | 2 | Rory and Neil | Completed | 2 | 2 | 2 | 1 | 1 | 1 | 0
Pair Programming, write code to past tests | 5 | Neil and Rory | Completed | 5 | 5 | 4 | 3 | 2 | 1 | 0
Pair Programming, program a new tab | 3 | Kurtis and Calum | Completed | 3 | 3 | 2 | 2 | 1 | 1 | 0
Pair programming, write function to rank shares | 4 | Rory and Neil | Completed | 4 | 4 | 2 | 3 | 2 | 2 | 0
Run function on android phone | 1 | Neil | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0
Pair programming, make font bigger for glance reading | 2 | Kurtis and Calum | Completed | 2 | 2 | 1 | 1 | 1 | 1 | 0
Pair Programming, Fix errors and handling | 3 | Calum and Kurtis | Completed | 3 | 3 | 2 | 2 | 1 | 2 | 0
Pair programming, refactor code | 4 | Rory and Neil | Completed | 4 | 4 | 4 | 3 | 3 | 2 | 0
Present completed task to customer | 1 | Team | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1
Ideal - Remaining efforts in uninterrupted working hours | 105 |  |  | 30 | 25 | 20 | 15 | 10 | 5 | 0
Actual - Remaing efforts in uninterrupted working hours | 118 |  |  | 26 | 26 | 20 | 18 | 14 | 13 | 1