## Sheet1
TEAM MC/DJ - SPRINT BACKLOG
NOT STARTED
IN PROGRESS
COMPLETED
3rd October - Thursday 14th October
Sprint 1 - TASK DESCRIPTION | Descripton (time in hrs) | Who? | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thur
1.1 Project preparation
Research use of Android SDK for displaying share information | 12 | M |  | 12 | 8 | 6 | 2 | 0 | 0 | 0 | 0 | 0
Research Use of Google Finance API for task | 4 | D |  | 4 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0
Download & Install Eclipse IOE/ANDROID | 2 | D |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 Coding
Obtain Share Values from API | 1 | M |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Display Total Share Worth | 1 | C |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Design + Implement User Interface | 1 | D |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Coding standards & Team Agreements | 1 | J |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 Testing
Calculate & Validate Data (testing) | 2 | J |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
Spring 1: Total Hours remaining | 24 |  |  | 23 | 17 | 15 | 10 | 6 | 5 | 3 | 1 | 0